## Design
Figma Design | Figma Designs
Sr no | Screen Description | Screen No
1 | Welcome Screen | 2023-01-03
2 | Login Functionality | 3
3 | Sign Up Screens | 2023-04-06
4 | Forgot Password | 2023-07-10
5 | Home Page | 11
6 | My Rooms | 12
7 | Create a Room | 13-14
8 | Notification | 15
9 | Edit Profile Functionality | 16-20
10 | Reset Password | 21-22
11 | Delete Account | 23-24

## Test Scenarios
Project Name | Keep It Going App
Reference Document | Design
Created By | Saurabh
Creation Date | 4th Dec 2023
Approval Date
Test Scenario ID | Refernce | Test Scenario Description | Number of Test Cases
TS_001 | Design | Validate the working of Flash Screen Functionality | 31
TS_002 | Design | Validate the working of Log In Functionality | 8
TS_003 | Design | Validate the working of Forgot Password Functionality | 20
TS_004 | Design | Validate the working of Reset Password Functionality | 5
TS_005 | Design | Validate the working of Homepage Functionality | 20
TS_006 | Design | Validate the working My Story Functionality | 30
TS_007 | Design | Validate the working Completed Story Functionality | 33
TS_008 | Design | Validate the working Notification Functionality | 10
TS_009 | Design | Validate the working My Profile Functionality | 23
TS_010 | Design | Validate the working Sign Up Functionality | 20
TS_011 | Design | Validate the working Story Flow Functionality | 35
|  | Total | 235

## Test Cases
TEST CASES ( KEEP IT GOING )
Date | Test Scenario | Tc-ID | Description | Test Step | Excepted Result (ER) | Actual Result | Status | Developer Remark | QA Name
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_001 | Onboarding Screen Functionality | 1) Open the App | App should be open | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_002 | Verify flash screen appearance | 1) Open the App | The flash screen should display the app logo and/or branding elements prominently. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_003 | Verify flash screen duration | 1) Open the App | The flash screen should disappear after a specified duration (e.g., 2 seconds). |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_004 | Verify flash screen animation | 1) Open the App | The flash screen animation should be smooth without any glitches or flickering. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_005 | Verify flash screen background color | 1) Open the App | The background color of the flash screen should match the app's design guidelines. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_006 | Verify flash screen on different devices | 1) Open the App | The flash screen should scale and display correctly on various screen resolutions and sizes. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_007 | Verify flash screen interaction | 1) Open the App | The flash screen should be non-interactive and not respond to touch gestures. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_008 | Verify flash screen behavior during app launch | 1) Open the App | The flash screen should appear instantly when launching the app. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_009 | Verify flash screen is skippable | 1) Open the App | The user should be able to skip the flash screen by tapping a designated area or button. |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_010 | Verify flash screen audio | 1) Open the App | If the flash screen contains sound effects, they should play correctly without distortion. |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_011 | Verify flash screen disappearance on user interaction | 1) Open the App | If the user taps the screen during the flash screen display, it should disappear immediately. |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_012 | Verify flash screen transition | 1) Open the App | After the flash screen disappears, the main app interface should appear smoothly. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_013 | Verify flash screen loading time | 1) Open the App | The flash screen should load quickly to provide a seamless user experience. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_014 | Verify flash screen consistency | 1) Open the App | The flash screen design and content should remain consistent across app launches. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_015 | Verify flash screen on different orientations | 1) Open the App | The flash screen should adapt correctly to landscape and portrait orientations. |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_016 | Verify flash screen behavior during app backgrounding | 1) Open the App | If the app is backgrounded and brought to the foreground, the flash screen should not reappear. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_017 | Verify flash screen during app interruptions (e.g., phone call) | 1) Open the App | If the app is interrupted during the flash screen display, it should resume afterward. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_018 | Verify flash screen in offline mode | 1) Open the App | The flash screen should still appear when the app is launched without an internet connection. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_019 | Verify flash screen with different internet speeds | 1) Open the App | The flash screen should load and display correctly regardless of the internet speed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_020 | Verify flash screen compatibility with different operating systems | 1) Open the App | The flash screen should work without issues across various supported OS versions. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_021 | Verify flash screen compatibility with different app versions | 1) Open the App | Upgrading the app should not cause any issues with the flash screen. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_022 | Verify flash screen alignment | 1) Open the App | The flash screen elements should be centered and aligned appropriately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_023 | Verify flash screen text readability | 1) Open the App | Any text on the flash screen should be easy to read and not cut off. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_024 | Verify flash screen consistency with the app's theme | 1) Open the App | The flash screen should match the overall theme and style of the app. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_025 | Verify flash screen behavior with different language settings | 1) Open the App | The flash screen should adapt to the user's language settings if applicable. |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_026 | Verify flash screen compatibility with accessibility settings | 1) Open the App | The flash screen should be accessible to users with disabilities. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_027 | Verify flash screen with different color themes | 1) Open the App | If the app supports various color themes, the flash screen should adhere to the chosen theme. |  | Not Included in Scope |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_028 | Verify flash screen branding consistency | 1) Open the App | The flash screen should reflect the correct branding elements of the app. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_029 | Verify flash screen exit options | 1) Open the App | If the flash screen is skippable, the user should be able to exit it without any issues. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_030 | Verify flash screen behavior during app updates | 1) Open the App | Updating the app should not affect the display or functionality of the flash screen. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_001) Flash Screen Functionality | Tc_031 | Verify flash screen performance impact | 1) Open the App | The flash screen should not cause any significant performance impact on the app's loading time. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_032 | Valid Username and Password: | Open the app. Enter a valid username. Enter a valid password. Click on the login button. | User should be successfully logged in. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_033 | Invalid Username: | Open the app. Enter an invalid username. Enter a valid password. Click on the login button. | App should display an error message indicating invalid username. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_034 | Invalid Password: | Open the app. Enter a valid username. Enter an invalid password. Click on the login button. | App should display an error message indicating invalid password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_035 | Empty Username: | Open the app. Leave the username field empty. Enter a valid password. Click on the login button. | App should display an error message indicating that the username field is required. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_036 | Empty Password: | Open the app. Enter a valid username. Leave the password field empty. Click on the login button. | App should display an error message indicating that the password field is required. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_037 | Incorrect Username and Password Combination: | Open the app. Enter an incorrect username. Enter an incorrect password. Click on the login button. | App should display an error message indicating invalid username or password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_038 | Case Sensitivity Check for Username: | Open the app. Enter a valid username in mixed case (e.g., "UsErNaMe"). Enter a valid password. Click on the login button. | App should treat the username as case-sensitive and display an error for incorrect case. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_002) LogIn Functionality | Tc_039 | Case Sensitivity Check for Password: | Open the app. Enter a valid username. Enter a valid password in mixed case (e.g., "PaSsWoRd"). Click on the login button. | App should treat the password as case-sensitive and display an error for incorrect case. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_040 | Valid Email Address | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. | User receives a password reset email. Confirmation message is displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_041 | Invalid Email Address | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter an invalid email address (e.g., without '@' symbol). Click on the "Submit" button. | User receives an error message indicating that the email address is invalid. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_042 | Email Address with Spaces | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter an email address with spaces. Click on the "Submit" button. | User receives an error message indicating that the email address is invalid. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_043 | Blank Email Address | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Leave the email address field blank. Click on the "Submit" button. | User receives an error message indicating that the email address is required. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_044 | Password Reset Email Delivery Time | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Check the email inbox for the password reset email. | Password reset email is delivered within a reasonable timeframe (e.g., a few minutes). | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_045 | Password Reset Link Expiration | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Wait for some time beyond the reset link expiration period. Click on the password reset link in the email. | User receives an error message indicating that the reset link has expired. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_046 | Reset Password with Valid Token | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Open the password reset email and click on the provided link. Enter a new password. Click on the "Submit" button. | Password is successfully reset. Confirmation message is displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_047 | Reset Password with Invalid Token | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Open the password reset email and use an invalid or expired link. Enter a new password. Click on the "Submit" button. | User receives an error message indicating that the reset link is invalid. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_048 | Password Reset Link Security | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Check the password reset email for security features (e.g., expiration time, one-time use). | Password reset link has appropriate security measures. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_049 | Cancel Password Reset | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Cancel" or "Go Back" button before clicking the link in the email. | Password reset process is canceled, and the user remains on the login screen. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_050 | Verify Password Complexity | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Open the password reset email and try setting a weak password. Click on the "Submit" button. | User receives an error message if the new password does not meet complexity requirements. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_051 | Change Password Success | Open the app. Log in with the old password. Navigate to the "Change Password" section in the app settings. Enter the old password, new password, and confirm the new password. Click on the "Submit" or "Change Password" button. | Password is successfully changed. Confirmation message is displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_052 | Change Password Failure - Incorrect Old Password | Open the app. Log in with the old password. Navigate to the "Change Password" section in the app settings. Enter an incorrect old password, new password, and confirm the new password. Click on the "Submit" or "Change Password" button. | User receives an error message indicating that the old password is incorrect. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_053 | Change Password Failure - Blank Fields | Open the app. Log in with the old password. Navigate to the "Change Password" section in the app settings. Leave the old password, new password, or confirm new password fields blank. Click on the "Submit" or "Change Password" button. | User receives an error message indicating that all fields are required. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_054 | Change Password Failure - Weak New Password | Open the app. Log in with the old password. Navigate to the "Change Password" section in the app settings. Enter a new password that does not meet complexity requirements. Click on the "Submit" or "Change Password" button. | User receives an error message indicating that the new password is too weak. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_055 | Security of Password Change Confirmation | Open the app. Log in with the old password. Change the password. Log out. Attempt to log in with the old password. | User is unable to log in with the old password after it has been changed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_056 | Password Recovery Option After Change | Open the app. Change the password. Log out. Attempt to log in with the old password. Click on the "Forgot Password" link. | User can initiate the password recovery process after changing the password and forgetting it. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_057 | Multiple Password Reset Requests | Open the app. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Repeat steps 2-4 with the same email address before using the first reset link. | Only the latest password reset link is valid. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_058 | Concurrent Password Reset Requests | Open the app. Click on the "Forgot Password" link. Enter a valid email address. Click on the "Submit" button. Repeat steps 2-4 with the same email address while the first reset link is still valid. | Only the latest password reset link is valid, and the previous links become invalid. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_003) Forgot Password Functionality | Tc_059 | Password Reset via Security Questions | Open the app. Navigate to the login screen. Click on the "Forgot Password" link. Choose the option for password recovery via security questions. Answer the security questions correctly. Enter a new password. Click on the "Submit" button. | User's password is successfully reset using security questions. Confirmation message is displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_004) Reset Password Functionality | Tc_060 | Successful Password Reset | Open the Android app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address associated with the account. Check the email for the password reset link. Click on the password reset link. Enter a new password in the "New Password" field. Re-enter the new password in the "Confirm Password" field. Click on the "Reset Password" button. | The app should confirm the password reset. The user should be able to log in using the new password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_004) Reset Password Functionality | Tc_061 | Password Mismatch | Open the Android app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address associated with the account. Check the email for the password reset link. Click on the password reset link. Enter a new password in the "New Password" field. Enter a different password in the "Confirm Password" field. Click on the "Reset Password" button. | The app should display an error message indicating that the passwords do not match. The user should not be able to reset the password until the passwords match. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_004) Reset Password Functionality | Tc_062 | Weak Password Validation | Open the Android app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address associated with the account. Check the email for the password reset link. Click on the password reset link. Enter a weak password in the "New Password" and "Confirm Password" fields. Click on the "Reset Password" button. | The app should display an error message indicating that the password is too weak. The user should be prompted to enter a stronger password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_004) Reset Password Functionality | Tc_063 | Blank Password Fields | Open the Android app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address associated with the account. Check the email for the password reset link. Click on the password reset link. Leave the "New Password" and "Confirm Password" fields blank. Click on the "Reset Password" button. | The app should display an error message indicating that the password fields cannot be blank. The user should be prompted to enter a password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_004) Reset Password Functionality | Tc_064 | Cancel Password Reset | Open the Android app. Navigate to the login screen. Click on the "Forgot Password" link. Enter a valid email address associated with the account. Check the email for the password reset link. Click on the password reset link. Click on the "Cancel" or "Go Back" button before entering a new password. | The app should cancel the password reset process. The user should remain on the login screen without changing the password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_065 | Verify User Name Title | Launch the app. Navigate to the home page. | The user's name/title is displayed correctly on the home page. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_066 | Verify Banner Image | Open the app. Check for the presence of the banner image. | The banner image is displayed, and it is relevant to the storytelling theme. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_067 | Verify Get Started Button | Navigate to the home page. Look for the "Get Started" button. Click on the "Get Started" button. | The app responds appropriately, and the user is directed to the relevant page or action. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_068 | Verify Story Rooms | Go to the home page. Check for the existence of Story Rooms. | Story Rooms are displayed, and they are populated with relevant content. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_069 | Verify Friend Request Section | Access the home page. Check for the presence of the Friend Request section. | Friend requests, if any, are displayed with appropriate information. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_070 | Verify My Story Button | Navigate to the home page. Look for the "My Story" button. Click on the "My Story" button. | The app navigates to the user's personal storytelling section. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_071 | Verify Create Story Button | Go to the home page. Check for the presence of the "Create Story" button. Click on the "Create Story" button. | The app opens the story creation interface. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_072 | Verify Notification Section | Access the home page. Check for the presence of the Notification section. | Notifications are displayed accurately with relevant information. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_073 | Verify My Profile Section | Navigate to the home page. Look for the "My Profile" section. Click on "My Profile." | The user's profile is displayed with accurate details. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_074 | Verify Navigation Between Section | Navigate between different sections on the home page Ensure smooth transitions | Smooth navigation without crashes or unexpected behavior. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_075 | Verify Responsiveness | Open the app on different Android devices. Check the responsiveness of UI elements on various screen sizes | UI elements are properly scaled and displayed on different devices. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_076 | Verify Interaction with Banner Image | Tap on the banner image | Banner image responds appropriately, leading to the intended action or screen. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_077 | Verify Story Room Content | Enter a Story Room. Check the content for accuracy and relevance | Story Room content is displayed correctly. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_078 | Verify Friend Request Acceptance | Receive a friend request. Accept the friend request | The story request is accepted and story is added to homepage and the appropriate notification is displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_079 | Verify My Story Content | Check the content under "My Story." | Personal storytelling content is displayed accurately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_080 | Verify Story Creation Process | Create a new story. Verify all steps in the story creation process. | A new story is created successfully without errors. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_081 | Verify Notification Handling | Receive a notification. Click on the notification. | The app navigates to the relevant section or action as indicated by the notification. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_082 | Verify Profile Editing | Go to the "My Profile" section. Edit profile information | Profile information is updated correctly. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_083 | Verify Logout Functionality | Log out of the app. Attempt to access restricted sections | User is successfully logged out, and restricted sections are inaccessible. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_005) Homepage Functionality | Tc_084 | Verify Error Handling | Intentionally trigger errors (e.g., no internet connection). | App displays appropriate error messages and handles errors gracefully. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_085 | Verify Title Display | Open the Story Page. Check if the title of the page is displayed at the top. | The title should be visible and correctly labeled. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_086 | Check Title Font and Size | Inspect the font style and size of the title. | The title should have a readable font and appropriate size. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_087 | Verify Title Alignment | Ensure the title is centered on the page. | The title should be aligned in the center. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_088 | Check Categories Section Presence | Look for the categories section on the page. | Active, Upcoming, and Completed categories should be visible. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_089 | Verify Active Category | Click on the Active category. | The content displayed should be stories that are currently active. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_090 | Verify Upcoming Category | Click on the Upcoming category. | The content displayed should be stories that are scheduled for the future. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_091 | Verify Completed Category | Click on the Completed category. | The content displayed should be stories that have been completed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_092 | Check Category Sorting | Add stories to each category with different timestamps. Verify the order of stories in each category. | Stories should be sorted in chronological order within each category. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_093 | Verify Story Rooms Display | Check if the Story Rooms section is visible. | Story Rooms should be displayed on the page. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_094 | Verify Story Room Card Elements | Click on a story room card. Ensure that the title, creator, and other relevant details are present. | All necessary information about the story room should be displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_095 | Check Story Room Card Images | Verify that the images associated with each story room are loaded properly. | Images should be displayed without any distortion or errors. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_096 | Verify Story Room Card Interaction | Click on a story room card. Check if it navigates to the detailed view of the story room. | The user should be taken to the detailed view of the selected story room. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_097 | Check Story Room Creation Time | Create a new story room. Verify that the creation time is correctly displayed on the Story Page. | The creation time should be visible and accurate. | As Per Expectations | Not In Scope |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_098 | Verify Completed Story Room Visibility | Complete a story room. Check if the completed story room is still visible in the Completed category. | The completed story room should be visible in the Completed category. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_099 | Check Empty State for No Story Room | Remove all story rooms from the user's account. Verify that an appropriate message or image is displayed when there are no story rooms. | A clear message should inform the user that there are no story rooms. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_100 | Verify Back Button Functionality | Click on the back button (if available) on the Story Page. | The app should navigate back to the previous screen. | As Per Expectations | Not In Scope |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_101 | Check Page Responsiveness | Rotate the device between landscape and portrait modes. Check if the Story Page elements adjust properly. | The Story Page should be responsive to different device orientations. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_102 | Verify Refresh Functionality | Pull down to refresh the Story Page. Verify that the content is updated. | The page should refresh, and the latest data should be displayed. | As Per Expectations | Not In Scope |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_103 | Check for Network Disconnection | Turn off network connectivity. Open the Story Page. | A message should inform the user about the lack of network connectivity. | As Per Expectations | Not In Scope |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_104 | Verify Loading Spinner | Introduce a delay in fetching data (simulate slow network). Verify if a loading spinner is displayed. | A loading spinner should be visible while data is being fetched. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_105 | Check for App Crashes | Perform various interactions rapidly. Monitor for any app crashes. | The app should not crash under normal usage conditions. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_106 | Verify Deep Linking | Click on a story room link from an external source. Verify if the app opens directly to the corresponding story room. | Deep linking should navigate the user to the specified story room. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_107 | Check Memory Usage | Monitor the app's memory usage while navigating the Story Page. | Memory usage should not excessively increase during normal usage. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_108 | Verify Offline Mode | Go offline after loading the Story Page. Attempt to interact with the page. | The app should display a message indicating that it's offline and limit interactions. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_109 | Check for Accessibility | Use accessibility tools to navigate the Story Page. Verify that all elements are accessible and provide meaningful information. | The app should be accessible to users with disabilities. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_110 | Verify Search Functionality | If the app has a search feature, test it on the Story Page. Search for a specific story room. | The search should return relevant results. | As Per Expectations | Not In Scope |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_111 | Check for Notification Handling | Send a notification related to a story room. Verify that clicking on the notification opens the correct story room. | Notifications should lead to the corresponding story room. | As Per Expectations | Not In Scope |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_112 | Verify Share Functionality | Share a story room from the Story Page. Verify that the shared content includes accurate details. | The shared content should accurately represent the story room. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_113 | Check for Security | Attempt to access the Story Page without proper authentication. | Unauthorized users should be prevented from accessing the Story Page. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_006) My Story Functionality | Tc_114 | Verify Navigation to Other Pages | From the Story Page, navigate to other pages of the app. Check if navigation is smooth and consistent. | Users should be able to navigate seamlessly between different sections of the app. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_115 | Valid Room Creation | Open the app. Navigate to the "Create Story Room" section. Fill in all the required fields (Title, Story Name, Genre/Theme, Select Starter, Story Description, No Of Rounds, Add Participants, Invite Friends). Click on the "Create Room" button. | The room should be successfully created, and the user should be redirected to the newly created room. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_116 | Missing Mandatory Information | Open the app. Navigate to the "Create Story Room" section. Leave one or more mandatory fields empty. Click on the "Create Room" button. | The app should display an error message indicating that all mandatory fields must be filled. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_117 | Invalid Characters in Title or Story Name | Open the app. Navigate to the "Create Story Room" section. Enter special characters or numbers in the Title or Story Name. Click on the "Create Room" button. | The app should display an error message indicating that the Title and Story Name should only contain letters. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_118 | Selecting Starter from Existing Stories | Open the app. Navigate to the "Create Story Room" section. Select a starter from the list of existing stories. Click on the "Create Room" button. | The room should be successfully created with the selected starter. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_119 | Validating No Of Rounds | Open the app. Navigate to the "Create Story Room" section. Enter a valid number for "No Of Rounds." Click on the "Create Room" button. | The room should be successfully created with the specified number of rounds. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_120 | Adding Participants | Open the app. Navigate to the "Create Story Room" section. Add one or more participants to the room. Click on the "Create Room" button. | The room should be successfully created with the added participants. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_121 | Inviting Friends | Open the app. Navigate to the "Create Story Room" section. Click on "Invite Friends" and select friends to invite. Click on the "Create Room" button. | The room should be successfully created, and invitations should be sent to the selected friends. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_122 | Creating Room without Participants | Open the app. Navigate to the "Create Story Room" section. Do not add any participants. Click on the "Create Room" button. | The app should display a warning or error message indicating that at least one participant is required. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_123 | Cancel Room Creation | Open the app. Navigate to the "Create Story Room" section. Fill in the required fields. Click on the "Cancel" or "Back" button. | The app should return to the previous screen, and no room should be created. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_124 | Verify Title Field | Launch the app and navigate to the "Start Story Room" section. Enter a valid title in the Title field. Verify if the title is displayed correctly. | The entered title should be displayed accurately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_125 | Verify Story Name Field | Navigate to the "Start Story Room" section. Enter a unique and valid name for the story in the Story Name field. Verify if the entered story name is displayed correctly. | The entered story name should be displayed accurately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_126 | Verify Genre/Theme Selection | Access the "Start Story Room" section. Select a genre or theme from the available options. Verify if the chosen genre/theme is displayed correctly. | The selected genre/theme should be displayed accurately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_127 | Verify Story Description Field | Open the "Start Story Room" section. Provide a detailed description of the story in the Story Description field. Verify if the entered story description is displayed correctly. | The entered story description should be displayed accurately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_128 | Verify Edit Participants Button | Go to the "Start Story Room" section. Click on the "Edit" button to add participants. Verify if the participant addition interface is displayed. | The participant addition interface should be accessible for editing. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_129 | Verify Start Storytelling Button | Navigate to the "Start Story Room" section. Ensure all mandatory fields are filled. Click on the "Start Storytelling" button. Verify if the user is directed to the storytelling interface. | The user should be redirected to the storytelling interface, confirming the initiation of the story. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_130 | Verify Blank Fields Validation | Open the "Start Story Room" section. Attempt to click on the "Start Storytelling" button without filling in any mandatory fields. Verify if appropriate validation messages are displayed for each empty field. | Validation messages should be shown for each mandatory field, and the button should not proceed without completing them. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_131 | Verify the "End Story" button is visible | Open the Story Telling App on your Android device. Navigate to the Story Room or the screen where the story is being created. Look for the "End Story" button. | The "End Story" button should be visible on the screen. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_132 | Confirm "End Story" button functionality | Open the Story Telling App on your Android device. Start creating a story in the Story Room. Once the story is in progress, tap on the "End Story" button. | The app should prompt the user with a confirmation dialog to confirm ending the story. If confirmed, the app should end the story and navigate the user to an appropriate screen (e.g., the main story list screen). | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_133 | Check for warning on unsaved changes | Open the Story Telling App on your Android device. Start creating a story in the Story Room. Make changes to the story but do not save them. Attempt to tap on the "End Story" button. | The app should display a warning or confirmation dialog notifying the user about unsaved changes. The user should have the option to save the changes, discard them, or cancel the "End Story" action. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_134 | Test "End Story" with a completed story | Open the Story Telling App on your Android device. Create and complete a story in the Story Room. Tap on the "End Story" button. | The app should end the story without any issues. The user should be navigated to an appropriate screen, such as the main story list or a summary screen for the completed story. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_135 | Verify "End Story" behavior in offline mode | Open the Story Telling App on your Android device. Disable network connectivity (turn off Wi-Fi and mobile data). Start creating a story in the Story Room. Attempt to tap on the "End Story" button. | The app should handle the action gracefully, considering the offline mode. The user should be notified that the action cannot be completed due to the lack of network connectivity. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_136 | Check for system interruptions during "End Story" | Open the Story Telling App on your Android device. Start creating a story in the Story Room. Initiate the "End Story" action. Interrupt the process with a system event (e.g., incoming call, low battery). | The app should handle system interruptions gracefully. The user should not experience any data loss or unexpected behavior when returning to the app after the interruption. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_137 | Give a positive reaction to a story message | Open the Storytelling App on your Android device. Navigate to the Room where the story is being told. Read a story message. Tap on the reaction button (emoji icon). Select a positive emoji reaction (e.g., thumbs up 👍). Verify that the emoji reaction is displayed next to the story message. Ensure that the total count of reactions is updated accordingly. | The positive emoji reaction is successfully applied to the story message, and the count is incremented. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_138 | Give a negative reaction to a story message | Open the Storytelling App on your Android device. Navigate to the Room where the story is being told. Read a story message. Tap on the reaction button (emoji icon). Select a negative emoji reaction (e.g., thumbs down 👎). Verify that the emoji reaction is displayed next to the story message. Ensure that the total count of reactions is updated accordingly. | The negative emoji reaction is successfully applied to the story message, and the count is incremented. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_139 | Remove a reaction from a story message | Open the Storytelling App on your Android device. Navigate to the Room where the story is being told. Read a story message that has a reaction. Tap on the reaction button (emoji icon). Tap on the already selected emoji to remove the reaction. Verify that the emoji reaction is no longer displayed next to the story message. Ensure that the total count of reactions is decremented. | The emoji reaction is successfully removed from the story message, and the count is decremented. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_140 | Give multiple reactions to a story message | Open the Storytelling App on your Android device. Navigate to the Room where the story is being told. Read a story message. Tap on the reaction button (emoji icon). Select multiple emoji reactions (e.g., heart ❤️, laughing 😄). Verify that all selected emoji reactions are displayed next to the story message. Ensure that the total count of reactions reflects the sum of individual reactions. | Multiple emoji reactions are successfully applied to the story message, and the count is updated accordingly. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_141 | Test for system response to invalid actions | Open the Storytelling App on your Android device. Navigate to the Room where the story is being told. Attempt to give a reaction without reading a story message. Verify that the app handles the action gracefully, possibly with an error message or notification. | The app should prevent giving a reaction without reading a story message and provide a clear error message or notification. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_142 | Save Story Functionality | Open the Storytelling App. Navigate to the "Story Complete" page. Write a new story or select an existing one. Click on the "Save" button. | The story should be saved successfully. Verify that a confirmation message appears, indicating that the story has been saved. Check the saved stories section to ensure the story is present. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_143 | Share on Social Media | Open the Storytelling App. Navigate to the "Story Complete" page. Write a new story or select an existing one. Click on the "Share" button. Choose a social media platform (e.g., Facebook, Twitter, Instagram) to share the story. | The app should open the selected social media platform. The story should be shared successfully on the chosen platform. Check the shared post on the social media platform to verify the content. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_144 | Cancel Saving a Story | Open the Storytelling App. Navigate to the "Story Complete" page. Write a new story or select an existing one. Make changes to the story. Click on the "Save" button. When prompted to confirm saving, click on the "Cancel" button. | The changes should not be saved. The user should remain on the "Story Complete" page with the original content intact. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_145 | Share Without Internet Connection | Disable the internet connection on the device. Open the Storytelling App. Navigate to the "Story Complete" page. Write a new story or select an existing one. Click on the "Share" button. Choose a social media platform to share the story. | The app should notify the user that there is no internet connection. The sharing process should be halted, and the user should be prompted to connect to the internet. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_146 | Verify Shared Story Appearance | Open the Storytelling App. Navigate to the "Story Complete" page. Write a new story or select an existing one. Click on the "Share" button. Share the story on a social media platform. Open the shared story link from the social media platform. | The shared story should open and display correctly. All elements, including text and media, should be visible and formatted appropriately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_007) Create Story Room Functionality | Tc_147 | Verify Saved Story Appearance | Open the Storytelling App. Navigate to the "Saved Stories" section. Confirm that a previously saved story is present. Click on the saved story to open it. | The saved story should open successfully. All elements, including text and media, should be visible and formatted appropriately. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_148 | Notification Display | Open the Storytelling App. Navigate to the Notification Page. | The Notification Page should display a list of notifications, if any. Each notification should include the sender's name, a brief message, and the timestamp. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_149 | Notification Sorting | Send multiple notifications from different users. Open the Notification Page. | Notifications should be sorted by timestamp in descending order, with the most recent notifications appearing at the top. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_150 | Mark All as Read | Receive multiple unread notifications. Open the Notification Page. Look for an option/button to "Mark All as Read" and select it. | All unread notifications should be marked as read. The notification count (if displayed) should reset to zero. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_151 | Individual Notification Read Status | Open the Notification Page. Check for unread notifications. Tap on an unread notification to view its details. | The selected notification should be marked as read. The notification count (if displayed) should decrement. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_152 | Notification Sound | Send a new notification to the user. Ensure the device's sound is enabled. Check for a notification sound when the notification arrives. | A distinct and recognizable notification sound should play when a new notification is received. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_153 | Notification Settings | Open the app's settings. Locate the notification settings section. Modify notification preferences (e.g., enable/disable sound, vibration, or push notifications). | Changes made to the notification settings should reflect in the behavior of notifications. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_154 | Notification Settings | Open the app's settings. Locate the notification settings section. Modify notification preferences (e.g., enable/disable sound, vibration, or push notifications). | Changes made to the notification settings should reflect in the behavior of notifications. |  | Not In Scope |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_155 | Clear All Notifications | Open the Notification Page. Look for an option/button to "Clear All" notifications and select it. | All notifications should be removed from the Notification Page. The notification count (if displayed) should reset to zero. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_156 | Notification Actions | Open a notification with actions (e.g., like, comment, share). Interact with the available actions (e.g., like the notification). | The selected action should be performed successfully. The notification details should update to reflect the action taken. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_008) Notification Functionality | Tc_157 | Push Notification Reliability | Ensure the app is closed or in the background. Send a push notification to the device. | The push notification should be received promptly, even if the app is not actively running. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_158 | Verify that the user can successfully upload a new profile photo. | Navigate to the Profile Photo section. Choose a new photo. Save or submit the changes. | The profile photo is updated, and the new image is displayed. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_159 | Attempt to update the profile photo with an unsupported file format. | Navigate to the Profile Photo section. Choose a file with an unsupported format (e.g., txt file). Save or submit the changes. | An error message is displayed, and the photo remains unchanged. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_160 | Try updating the profile photo with an excessively large file size. | Navigate to the Profile Photo section. Choose a photo with a large file size. Save or submit the changes. | An error message is displayed, prompting the user to choose a smaller file. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_161 | Verify that the user can update profile details such as name, bio, and other information. | Navigate to the Profile Details section. Update one or more fields (e.g., name, bio). Save or submit the changes. | The profile details are updated, and the changes are reflected on the profile page. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_162 | Attempt to update the profile with invalid or empty information. | Navigate to the Profile Details section. Provide invalid or empty data in one or more fields. Save or submit the changes. | An error message is displayed, and the profile remains unchanged. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_163 | Verify that changes in profile details are immediately visible on the profile page. | Navigate to the Profile Details section. Update one or more fields. Check the profile page immediately. | The changes are reflected without the need for a manual refresh. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_164 | Successfully reset the password using a valid email address. | Navigate to the Reset Password section. Enter a valid email address. Follow the password reset instructions received via email. | The password is successfully reset, and the user can log in with the new password. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_165 | Attempt to reset the password with an invalid or unregistered email address. | Navigate to the Reset Password section. Enter an invalid or unregistered email address. Follow the password reset instructions received via email. | An error message is displayed, indicating that the email address is not recognized. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_166 | Verify that the password reset link expires after the specified time. | Request a password reset link. Wait for the specified time period. Attempt to use the expired link. | An error message is displayed, indicating that the link has expired. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_167 | Successfully delete the account after confirming the action. | Navigate to the Delete Account section. Confirm the account deletion. | The account is successfully deleted, and the user is logged out. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_168 | Attempt to delete the account without confirming the action. | Navigate to the Delete Account section. Cancel or navigate away without confirming deletion. | The account deletion is canceled, and the user remains logged in. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_169 | Verify that the user is automatically logged out after deleting the account. | Confirm the deletion of the account. Attempt to perform any action that requires authentication. | The user is redirected to the login page, indicating successful account deletion. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_170 | Ensure that the Terms and Conditions link is accessible from the Profile page. | Navigate to the Profile page. Click on the Terms and Conditions link. | The Terms and Conditions page opens without any errors. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_171 | Verify that the user can scroll through the entire content of the Terms and Conditions page. | Access the Terms and Conditions page. Scroll through the entire content. | The user can scroll through the entire content without any issues. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_172 | Check if the "Accept" button is functional after reading the Terms and Conditions. | Access the Terms and Conditions page. Read through the content. Click on the "Accept" button. | The user is redirected back to the Profile page, indicating successful acceptance of the terms. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_173 | Ensure that the Privacy Policy link is accessible from the Profile page. | Navigate to the Profile page. Click on the Privacy Policy link. | The Privacy Policy page opens without any errors. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_174 | Verify that the user can scroll through the entire content of the Privacy Policy page. | Access the Privacy Policy page. Scroll through the entire content. | The user can scroll through the entire content without any issues. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_175 | Check if the "Agree" button is functional after reading the Privacy Policy. | Access the Privacy Policy page. Read through the content. Click on the "Agree" button. | The user is redirected back to the Profile page, indicating successful agreement with the privacy policy. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_176 | Verify that the user can log out successfully from the Profile page. | Navigate to the Profile page. Click on the Logout button. | The user is logged out and redirected to the login page. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_177 | Attempt to access restricted pages after logging out. | Log out. Attempt to access a page that requires authentication. | The user is redirected to the login page, indicating successful logout. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_178 | Check if the app prompts for confirmation before logging out. | Click on the Logout button. | A confirmation dialog appears, asking the user to confirm the logout action. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_179 | Verify that the app does not crash or show errors after logging out. | Log out. Attempt to navigate through various pages. | The app remains stable, and no errors are displayed after logging out. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_009) My Profile Functionality | Tc_180 | Ensure that the app clears any locally stored user data upon logout. | Log in and perform some actions. Log out. Attempt to access the app without logging in again. | The app does not retain any user data after logout, and the user is prompted to log in again. | As Per Expectations | Pass |  | Sauarbh
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_181 | Validate successful sign up with all valid information. | Navigate to the sign-up page. Fill in valid values for Username, Firstname, Lastname, Email, Mobile, Password, and Gender. Click on the "Sign Up" button. | User is successfully registered and redirected to the home page. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_182 | Attempt sign up with an existing username. | Navigate to the sign-up page. Provide an existing username. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the username is already in use. | As Per Expectations | Not In Scope
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_183 | Attempt sign up with missing Email field. | Navigate to the sign-up page. Fill in valid values for Username, Firstname, Lastname, Mobile, Password, and Gender. Click on the "Sign Up" button. | Display an error message indicating that the Email field is required. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_184 | Attempt sign up with an invalid email format. | Navigate to the sign-up page. Fill in valid values for all fields with an invalid email format. Click on the "Sign Up" button. | Display an error message indicating that the email format is invalid. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_185 | Attempt sign up with missing Mobile field. | Navigate to the sign-up page. Fill in valid values for Username, Firstname, Lastname, Email, Password, and Gender. Click on the "Sign Up" button. | Display an error message indicating that the Mobile field is required. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_186 | Attempt sign up with an invalid mobile number. | Navigate to the sign-up page. Fill in valid values for all fields with an invalid mobile number. Click on the "Sign Up" button. | Display an error message indicating that the mobile number format is invalid. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_187 | Attempt sign up with a weak password. | Navigate to the sign-up page. Fill in valid values for all fields with a weak password. Click on the "Sign Up" button. | Display an error message indicating that the password is weak. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_188 | Attempt sign up with missing Gender field. | Navigate to the sign-up page. Fill in valid values for Username, Firstname, Lastname, Email, Mobile, Password. Click on the "Sign Up" button. | Display an error message indicating that the Gender field is required. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_189 | Attempt sign up with all fields empty. | Navigate to the sign-up page. Leave all fields empty. Click on the "Sign Up" button. | Display error messages for all required fields. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_190 | Verify the case sensitivity of the Username field. | Navigate to the sign-up page. Enter a username in a mix of uppercase and lowercase letters. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | The system should treat the username as case-insensitive and register the user successfully. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_191 | Attempt sign up with a very long Firstname. | Navigate to the sign-up page. Enter a Firstname with a length exceeding the allowed limit. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the Firstname is too long. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_192 | Attempt sign up with a very long Lastname. | Navigate to the sign-up page. Enter a Lastname with a length exceeding the allowed limit. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the Lastname is too long. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_193 | Attempt sign up with a special character in the Username. | Navigate to the sign-up page. Enter a Username with a special character (e.g., @, #, $). Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the Username can only contain alphanumeric characters. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_194 | Attempt sign up with a valid email from a restricted domain. | Navigate to the sign-up page. Enter a valid email from a restricted domain (e.g., example@restricted.com). Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the email domain is not allowed. |  | Not In Scope
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_195 | Verify the visibility of the entered password. | Navigate to the sign-up page. Enter a password. Check if the entered password is visible. Click on the "Sign Up" button. | The entered password should be hidden/obscured for security reasons. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_196 | Verify the maximum character limit for the Password field. | Navigate to the sign-up page. Enter a password exceeding the allowed character limit. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the password is too long. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_197 | Attempt sign up with a valid but already used email. | Navigate to the sign-up page. Enter a valid email that is already associated with an existing account. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | Display an error message indicating that the email is already in use. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_198 | Attempt sign up without accepting the Terms of Service. | Navigate to the sign-up page. Fill in valid values for all fields. Do not check the "Accept Terms of Service" checkbox. Click on the "Sign Up" button. | Display an error message indicating that the Terms of Service must be accepted. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_199 | Verify the case sensitivity of the Email field. | Navigate to the sign-up page. Enter an email address in a mix of uppercase and lowercase letters. Fill in valid values for the remaining fields. Click on the "Sign Up" button. | The system should treat the email address as case-insensitive and register the user successfully. | As Per Expectations | Pass
2023-12-04 | (TS_0010) Sign Up Functionality | Tc_200 | Attempt sign up with a valid password but missing other required fields. | Navigate to the sign-up page. Enter a valid password. Leave other required fields (Username, Firstname, Lastname, Email, Mobile, Gender) empty. Click on the "Sign Up" button. | Display error messages for all the missing required fields. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_201 | 0 | Navigate to player invitation section. Input email addresses of players to invite. Click "Invite". | Players receive invitations successfully. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_202 | First Player's Turn - Fill in the Blank | First player fills in the blank with one word. Submits the word. | Word is successfully submitted. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_203 | First Player's Turn - Story Continuation | First player continues the story within < 240 characters. | Story is continued effectively within the character limit. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_204 | Subsequent Player's Turn - Fill in the Blank | Subsequent player fills in the blank with one word. Submits the word. | Word is successfully submitted. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_205 | Subsequent Player's Turn - Story Continuation | Subsequent player continues the story within < 240 characters. | Story is continued effectively within the character limit. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_206 | Last Sentence - Blank for Next Player | Ensure the last sentence ends with a blank. | Last sentence has a blank for the next player to fill in. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_207 | Game Duration - No Set Time/Intervals | Start the game without specifying time intervals. Play the game. | Room Owner can end the game at any point without set time intervals. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_208 | Game Ending - Player Initiated | Player initiates the end of the game. | Game ends successfully upon player's request. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_209 | Game Ending - System Initiated | Game reaches predefined end conditions. | Game ends automatically as per predefined conditions. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_210 | Game Saving - Successful | End the game. Verify game is saved. | Game is successfully saved for future reference. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_211 | Share Options Availability | End the game. Check for share options (Facebook, email, etc.). | Share options are available for sharing the completed game. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_212 | Maximum Character Limit - Fill in the Blank | First player fills in the blank with more than allowed characters. | System correctly restricts input to the maximum character limit. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_213 | Maximum Character Limit - Story Continuation | First player's story continuation exceeds character limit. | System enforces character limit for story continuation. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_214 | Minimum Settings - One Player | Start the game with minimum settings (one player). | Game functions correctly with minimum settings. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_215 | Invite Players - Invalid Email Format | Input invalid email format in player invitation. Click "Invite". | System prompts for valid email format. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_216 | First Player's Turn - Blank Submission | First player leaves the blank field empty. Submits the word. | System prompts for a word to be filled in. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_217 | Subsequent Player's Turn - Blank Submission | Subsequent player leaves the blank field empty. Submits the word. | System prompts for a word to be filled in. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_218 | Game Ending - Unexpected Termination | Unexpected termination of the game application. | Game data is recovered upon restarting the application. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_219 | Game Saving - Error Handling | End the game with a network error. Verify game saving process. | System handles network error and retries saving. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_220 | Share Options - Social Media Integration | End the game. Share the game on social media platforms. | Game is successfully shared on social media platforms. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_221 | Player Disconnect - Reconnection | Player disconnects during the game. Reconnects to the game. | Player rejoins the game seamlessly without data loss. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_222 | Game Restart - Mid-Session | Restart the game in the middle of a session. | Game restarts from the last saved point. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_223 | Blank Field - Placeholder Text | Check for placeholder text in the blank field. | Placeholder text guides players to input one word. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_224 | Game Progression - Story Continuity | Check for smooth continuity of the story between players. | Story progresses logically and coherently. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_225 | Player Profile - Customization | Customize player profile settings. | Player profile settings are successfully updated. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_226 | Player Profile - Avatar Selection | Select avatar for player profile. | Avatar is displayed correctly in player profile. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_227 | Game Progression - Turn Rotation | Verify correct rotation of turns among players. | Turns rotate among players as per game rules. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_228 | Game Interruption - System Message | Check for system message in case of game interruption. | System message notifies players of game interruption. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_229 | Game Termination - Graceful Exit | Exit the game gracefully using the provided option. | Game exits without data loss or errors. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_230 | Game Termination - Unexpected Exit | Force close the game application unexpectedly. | Game data is recovered upon restarting the application. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_231 | Story Continuity - Multiple Blanks | Ensure the story has multiple blanks for players to fill in. | Each player fills in a different blank in the story. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_232 | Share Options - Email Integration | End the game. Share the game via email. | Game is successfully shared via email. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_233 | Share Options - No Connection | Attempt to share the game with no internet connection. | System prompts for an internet connection or retries when connection is available. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_234 | Game Interruption - Notification | Check for system notifications in case of game interruption. | System notifies players of game interruption through notifications. | As Per Expectations | Pass
2023-12-04 | (TS_0011) Story Flow Functionality | Tc_235 | Player Disconnect - Auto-Rejoin Attempt | Player disconnects during the game. Verify the system's attempt to auto-rejoin. | System attempts to reconnect the player automatically. | As Per Expectations | Pass

## Bug Sheet
BUG REPORT ( KEEP IT GOING )
Date Raised | Bug_ID | Test Module | Version | Description/ Bug Summary | Expected Result | Status | Severity ( Critical/Major/Medium/Low ) | Priority (P1/P2/P3/P4) | Date Closed | Test Excecuted By | Comment | developer status | developer comment
2024-03-12 | Bug_001 | My Story | 1 | Category i.e Active,Upcoming, Completed are not properly Visible | Please aligned it properly | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_002 | Sign Up | 1 | We can Select Gender option for selecting a gender | There should be only 3 option i.e Male, Female, Other | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_003 | Sign Up | 1 | Welcome Message can be little bit bold....It is not similar as figma |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_004 | Create Room | 1 | Change the spelling of Romance |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_005 | Create Room | 1 | We can Select Starter as Select any Starter | Select any Starter should not be an option | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_006 | Create Room | 1 | Change the No of Round into number not in words |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_007 | Create Room | 1 | Participants Avatar are properly visible | If possible make it more clear for better user experience | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | issue | not in proper svg format
2024-03-12 | Bug_008 | Create Room | 1 | Change Start StoryTelling to Start Story | It should be Stary Story to proceed the game | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_009 | Create Room | 1 | Chat Screen is not visible | User should able to view the screen with select/created starter | Fixed | Major | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_010 | My Profile | 1 | Logout Button is not working | User should able to Logout and Redirected to Login Screen | Fixed | Major | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_011 | My Profile | 1 | Profile Edit Button not working | User should able to Edit Profile Pic | Fixed | Major | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_012 | Reset Password | 1 | Hide Icon is not Working |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_013 | Sign Up | 1 | Width of Register Button is bigger | It can be little bit smaller, make it as per figma | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_014 | Sign Up | 1 | Email Verification Title can be bold | Make it as per figma | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_015 | Sign Up | 1 | Verify Button width should be as per figma | It can be little bit smaller, make it as per figma | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_016 | Forgot Password | 1 | Please minimize the size of email field and Send Code button | It can be little bit smaller, make it as per figma | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_017 | Homepage | 1 | Change Icon of My Story |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_018 | Homepage | 1 | Correct the Spelling of My Story | First letter of Story should be capital | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_019 | Homepage | 1 | Change the Icon of Notification |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_020 | Create Room | 1 | For Custom Starter Description Field there is not limit is shown | Below the Description box show message about word limit i.e 250 | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_021 | Create Room | 1 | In Add Participants search Box, Search Icon is not added | Refer figma and add it | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_022 | My Profile | 1 | Increase the Size of Profile Pic | Refer Figma, there is no space below log out btn. But In Apk we can see the space | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_023 | Manage Account | 1 | Decrease the Size of All the Field | It can be little bit smaller, make it as per figma | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_024 | Manage Account | 1 | Add Country option in Mobile number field | User should able to change the country code with selecting different country | Fixed | Medium | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_025 | Manage Account | 1 | Show the Option to select the Gender to update |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_026 |  | 1 | If possible Make sure we use same font in all the app as per figma.....Because change of font it is looking different while using and its not a good user experience |  | Fixed | Medium | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_027 | Sign Up | 1 | Highlight the Selected option when dropdown is open | If male is selected by user then in dropdown user should view male option selected | Fixed | Low | P2 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_028 | Create Room | 1 | Highlight the Selected option when dropdown is open |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_029 | Manage Account | 1 | Highlight the Selected option when dropdown is open for Gender |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_030 | Sign Up | 1 | In Sign Up Page, If Password eye button is open the password should be visible but currently it is not visible for user......It is visible when eye button is close that is not as per expected | When Eye button is open then only password should be visible....Change it vice versa | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_031 | Sign Up | 1 | In Mobile Field we cant clear the field | User should be able to clear the field details if he/she enter wrong details | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_032 | Sign Up | 1 | In Mobile Field when user enter details the automatically country code is entered | Details should be entered as per the user submit | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_033 | Sign Up | 1 | Cant create an User account | Please resolve the bugs to create a account | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_034 | Log In | 1 | In LogIn Up Page, If Password eye button is open the password should be visible but currently it is not visible for user......It is visible when eye button is close that is not as per expected | When Eye button is open then only password should be visible....Change it vice versa | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_035 | Sign Up | 1 | During Otp verification there is no resend Otp option given | User should able to resend otp to verify otp | Fixed | Major | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_036 | Sign Up | 1 | During Otp verification if user enters invalid otp then alert message comes up.....Delete unwanted message like Status, Success | Just show invalid otp alert message | Fixed | Critical | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_037 | My Account | 1 | Change the spelling of Gallery |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_038 | My Account | 1 | If user logout and login again then saved avatar of user is not reflecting as per register | Same avatar should be visible to user after multiple times login or logout | Fixed | Critical | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_039 | My Account | 1 | Country Code Selected while register is not reflecting in my account | Details should be similar as per registration details | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_040 | My Account | 1 | Country Code is added twice in mobile number field | Remove Country Code from mobile number as we given country code once | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_041 | Reset Password | 1 | In Reset Password Page, If Password eye button is open the password should be visible but currently it is not visible for user......It is visible when eye button is close that is not as per expected | When Eye button is open then only password should be visible....Change it vice versa | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_042 | Reset Password | 1 | Please check the placement of cursor |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_043 | My Account | 1 | Sudden Blank screen Occurs |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_044 | Forgot Password | 1 | Please check the placement of cursor |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_045 | Forgot Password | 1 | Otp gets validate with Invalid Otp | Invalid Otp should not accepted and user should get alert message | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_046 | Forgot Password | 1 | Please check the placement of cursor for new and confirm password fields |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_047 | Forgot Password | 1 | InForgot Password Confirmation Page, If Password eye button is open the password should be visible but currently it is not visible for user......It is visible when eye button is close that is not as per expected | When Eye button is open then only password should be visible....Change it vice versa | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_048 | Delete Account | 1 | Please give one Popup message to user to confirm if user wants to delete the account details permanently or not |  | Fixed | Medium | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_049 | Sign Up | 1 | Mobile Number Field accepts symbols | Field should accept only digits | Fixed | Medium | P1 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_050 | My Account | 1 | Mobile is viewed in default i.e Afghanistan | Country Code should be same as per selected during registration | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_051 | Homepage | 1 | If Storyrooms are not available then there should be message to create own story room | Refer Figma | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_052 | My Rooms | 1 | If Storyrooms are not available then there should be message to create own story room | Refer Figma | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_053 | Create Room | 1 | Mask appear on screen cant create story room | Mask is appearing sometimes not everytime | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_054 | Homepage | 1 | Clicking Create Story Room is static | Redirect to the Story Room Creation Page | Fixed | Medium | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_055 | My Rooms | 1 | Clicking Create Story Room is static | Redirect to the Story Room Creation Page | Fixed | Medium | P4 | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_056 | My Account | 1 | Mobile Number is shown value Null after user log in again | Mobile number should be same as per user register | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_057 | Create Room | 1 | Mask appear on screen cant create story room after entering all details |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_058 | My Story | 1 | Please add back button on page |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal |  |  | not needed
2024-03-12 | Bug_059 | Create Room | 1 | Please assign different theme colours to all different story room card colours |  | Fixed | Medium | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_060 | Create Room | 1 | Please check alignment of " Search By User ID or Email " in Add participants field | It is slighlty upright...Please align it to Center with search icon | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_061 | Create Room | 1 | If Participants is not added by room owner then proper alert message should be shown to user | " Atleast 1 participant has to be added to create a story room " Add this message | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_062 | Homepage | 1 | Button colour of button and card should be same as per figma |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_063 | Create Room | 1 | Button colour of theme should be same as per figma |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_064 | Create Room | 1 | Please maintain same colour combination for all themes |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_065 | Create Room | 1 | Thriller Button is started with lowercase letters | Every Button should start with Uppercase letter | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_066 | Create Room | 1 | When Room Owner add a participant and then unselect it.....And then click create room button then room is created with 0 number of participants | As participant is unselect there is 0 participants and if room owner try to create room he/she should get alert message to add atleast 1 participants | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_067 | Create Room | 1 | Pop up message when room is create should have uppercase letter only | Room word has lowercase letter in popup message | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_068 | Create Room -> Add Participants | 1 | In Add Participants search Box, Search Field is static | It should be dynamic | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_069 | Create Room -> Add Participants | 1 | In Add Participants Screen, Invite button is not added at participants which we are trying to add in our room |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal | done
2024-03-12 | Bug_070 | Create Room -> Add Participants | 1 | Back Button is not added in Add Participants screen |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | no need of button when there is already a bottom nav present
2024-03-12 | Bug_071 | Homepage | 1 | In Story Room Card, Starter is aligned to center | It should be aligned at left side....as starter description is minimum it will not give a good user experience | Fixed | Medium | P4 | 2024-03-13 | Saurabh, Komal | done
2024-03-12 | Bug_072 | Story Room Screen | 1 | Please add info button and more vert button |  | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal | ansh is working on it
2024-03-12 | Bug_073 | Story Room Screen | 1 | Please add back button on page | There is back button in figma desgin.. please make changes | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | no need of button when there is already a bottom nav present
2024-03-12 | Bug_074 | My Story | 1 | Please add back button on page | There is back button in figma desgin.. please make changes | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | no need of button when there is already a bottom nav present
2024-03-12 | Bug_075 | MyStory, Homepage | 1 | Error message comes up and page is not loading |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_076 | My Account | 1 | Mask appear in IOS device for some seconds and it disappears |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_077 | Homepage | 1 | In the request story the information icon story description card can be shown with better UI and proper alignment of card |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal | will ask designer to make a better one
2024-03-12 | Bug_078 | Homepage | 1 | Theme Button icon which is in request card has different colour than we have selected than figma... |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_079 | Chat Screen | 1 | There should be 2 chance for every chance i.e 1st and 2nd part of story .....But 1st part of story is static |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | ansh is working on it
2024-03-12 | Bug_080 | Chat Screen | 1 | Live message of other players are visible only when screen is changed | Message should be appear when other player send message | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_081 | Add Participants | 1 | There is no app links of Android and IOS for non existing user to join room |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | will do once the apps are live
2024-03-12 | Bug_082 | Chat Screen | 1 | There is No Option to End Story for Admin |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | ansh is working on it
2024-03-12 | Bug_083 | Create Room | 1 | Back Button is not added in Create Story Room back.....If user hits back button he/she will directly go out of the app | Please refer figma | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_084 | Room Card Screen | 1 | Story Room Card Image in Room Page is not properly fit and also its not looking clear....Its not a user experience | Please add clear image with proper fit | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_085 | Create Room | 1 | Mask Appear when new participant request has been made......Request is send successfully but room owner screen has mask |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_086 | Homepage | 1 | When Room Owner start the story without parcipants accepts the request....Then the participants try to join the room which is already started....User gets null error message when request is accepted | Instead of null message please proper message i.e Sorry! Story Room is started please to join/create another room | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal | can be fixed from backend
2024-03-12 | Bug_087 | My Profile | 1 | Back Button is not added in My Profile Page.....If user hits back button he/she will directly go out of the app |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_088 | Chat Screen | 1 | User avatar is static....It should be similar to which user has selected/saved while register or updated in profile |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal | ansh is working on it
2024-03-12 | Bug_089 | Chat Screen | 1 | Story Room Image is different in Homapage card view and different in story room chat screen |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal | ansh is working on it
2024-03-12 | Bug_090 | My Profile | 1 | Please show proper error message when limit is crossed in name fields |  | Fixed | Low | P3 | 2024-03-13 | Saurabh, Komal | fixed
2024-03-12 | Bug_091 | My Profile | 1 | If User Name is set in Upper case letter then in my profile it should be also display in uppercase letter |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | username should always be in lowercase
2024-03-12 | Bug_092 | Homepage | 1 | Colour Of the Family card is different |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | YOU CAN CHANGE IT TO ANY COLOR THROUGH ADMIN PANEL
2024-03-12 | Bug_093 | Homepage | 1 | Colour Of the Comedy card is different |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | YOU CAN CHANGE IT TO ANY COLOR THROUGH ADMIN PANEL
2024-03-12 | Bug_094 | Homepage | 1 | All combinations are changes for all genres...Please maintain same colour combination of story cards |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | YOU CAN CHANGE IT TO ANY COLOR THROUGH ADMIN PANEL
2024-03-12 | Bug_095 | Story Invitation Card | 1 | The romance genre tab is not visible in story invitation card |  | Fixed | Medium | P4 | 2024-03-13 | Saurabh, Komal | Done
2024-03-12 | Bug_096 | Homepage | 1 | The image is not properly fit in container for Story Room Card of Sci-Fi-Adventure |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal | There is an image restriction for that and its already there
2024-03-12 | Bug_097 | Homepage | 1 | If user does not have internet connection and if internet connection is restored then app does not refresh automatically...Error message comes up | Refresh the app as soon as internet connection is restored | Fixed | Medium | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_098 | Add Participants | 1 | If we add the participant and click Done button, suddenly done button changes to white colour | Colour of Done button should not change to white | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_099 | Add Participants | 1 | There is no invite button for users who are not register on application | Please add invite button front of email if email is not register | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal | You can add them directly no need to press 2 buttons to invite them
2024-03-12 | Bug_100 | Whole App | 1 | Need to be fixed to portrait mode only |  | Fixed | Critical | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_101 | Add Participants | 1 | If we try to invite a player after story room creation, the user cannot send an invitation for non existing user using an email...Error message comes up |  | Fixed | Critical | P2 | 2024-03-13 | Saurabh, Komal | Fixed
2024-03-12 | Bug_102 | Story Room Screen | 1 | No push and in app notification when story is started by room owner |  | Fixed | Medium | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_103 | Chat Screen | 1 | Emoji reactions are not displayed next to the story message. |  | Fixed | Medium | P3 | 2024-03-14 | Saurabh, Komal
2024-03-12 | Bug_104 | Chat Screen | 1 | After completing the number of rounds...The last player still has access to the keyboard for a few sec and the last turn is shown as typing...A number of rounds is completed so there should be no extra chance for the user | Refer video shared on grp | Fixed | Critical | P2 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_105 | Chat Screen | 1 | Share Card not working for android |  | Fixed | Critical | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_106 | Chat Screen | 1 | User can share story card without internet | The app should notify the user that there is no internet connection. The sharing process should be halted, and the user should be prompted to connect to the internet. | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_107 | My Profile | 1 | No error message when empty fields are saved | An error message should displayed, and the profile remains unchanged. | Fixed | Medium | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_108 | Chat Screen | 1 | If user lock his/her screen chat is not updated/refresh the updated chat...User need to change the screen to see updated chat | Check for the IOS app...Please refresh the chat screen as soon as the user open the lock screen and land on chat screen | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_109 | Chat Screen | 1 | No in-app notification for participants other than room owner when story is completed |  | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_110 | Chat Screen | 1 | During game if user changes profile image then in chat screen user profile image should update accordingly |  | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_111 | PushNotification | 1 | Game Start: "The story room has started! It's your turn to contribute." | This notification should comes when game is started not when turn of user comes | Fixed | Medium | P3 | 2024-03-14 | Saurabh, Komal | //backend can change it to whatever text
2024-03-12 | Bug_112 | PushNotification | 1 | Reminder to Contribute: "It's your turn! Add your part to the story now." | Instead of this game start notification is displayed | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_113 | PushNotification | 1 | Story Card Available, General Updates, Inactive Story Room | Not Working Please have a look | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal | We havent added it,Can be added by the backend anytime
2024-03-12 | Bug_114 | In App Notification on participants side | 1 | Story Room Invitation, Game Start, Participant Skipped, Game End | Not Receiving this in-app notification for participant other than room owner | Fixed | Medium | P3 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_115 | Delete Account | 1 | No mail after deleting an account |  | Fixed | Critical | P1 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_116 | My Profile | 1 | After Sign up, Based on gender default profile image should be shown | For male gender- Current image and for female and other options please add a different default image | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_117 | My Profile | 1 | 1) Room Owner can add, edit, delete user before and after story is created 2) Owner can delete/Skip turn user while on going story 3) Owner cant delete, add any user once story is completed | Consider all this scenarios | Fixed | Critical | Critical | 2024-03-13 | Saurabh, Komal |  | done
2024-03-12 | Bug_118 | Sign Up | 1 | In-app notification when OTP is sent to register email ID...All text in in-app notification should be in uppercase letter |  | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_119 | Chat Screen | 1 | Error Message - Error in getting game data please try again later | Occurs only 1 time...Please refer video from Group | Fixed | Critical | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_120 | Splash Screen | 1 | Photo is not displayed in 1st splash screen | Should be displayed a photo in 1st splash screen... | Fixed | Low | P4 | 2024-03-13 | Saurabh, Komal
2024-03-12 | Bug_121 | Delete Account->Login | 1 | When the User redirect to the login page after the account is deleted then error message comes up " Something went wrong " |  | Fixed | Critical | P1 | 2024-03-14 | Saurabh, Komal
2024-03-12 | Bug_122 | Delete Account | 1 | There is an issue while changing the game turn...The keyboard stuck at the user who delete account so players cant continue there story |  | Fixed | Critical | P1 | 2024-03-14 | Saurabh, Komal
2024-03-23 | Bug_123 | Sign Up | 1 | Attempt sign up with a very long Firstname. | Display an error message indicating that the Firstname is too long. | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_124 | Sign Up | 1 | Attempt sign up with a very long Lastname. | Display an error message indicating that the Lastname is too long. | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_125 | Sign Up | 1 | The maximum character limit for the Password field is allowed | Display an error message indicating that the password is too long. | Fixed | Medium | P4 | 2024-03-27 | Saurabh, Komal |  | Done
2024-03-23 | Bug_126 | Forgot Password | 1 | OTP expires then the user should not get an error message like invalid OTP.The error message should be " OTP is expired " | User receives an error message indicating that the reset link has expired. | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_127 | Forgot Password | 1 | Password field is accepting same old password | The same password should not be accepted and error message should appear to set new password other than previous password | Fixed | Medium | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_128 | Create Room | 1 | In the Story Starter dropdown, Custom option should be last in list |  | Fixed | Low | P4 | 2024-03-27 | Saurabh, Komal |  | Done
2024-03-23 | Bug_129 | Create Room | 1 | Remove validation for story name field | It should not have validation to not having space in story name | Fixed | Low | P4 | 2024-03-27 | Saurabh, Komal |  | Done
2024-03-23 | Bug_130 | Create Room | 1 | If user change the genre/theme the starter title and description should get clear |  | Fixed | Critical | P1 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_131 | Create Room | 1 | Cant create story room with valid details |  | Fixed | Critical | P1 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_132 | Story Invitation Card | 1 | In the Story Room Information page, the Genre/Theme tab should be prominent and information title should have a min size than genre tab |  | Fixed | Low | P4 | 2024-03-27 | Saurabh, Komal |  | Done
2024-03-23 | Bug_133 | Story Invitation | 1 | User needs to refresh the screen to view story room request |  | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_134 | Notification | 1 | The notification icon should have a count/mark to indicate user that new notification is arrived in notification section |  | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_135 | Add Participants | 1 | If the request is sent to a non-registered user through email...Then user should get a story invitation request after completing registration through same email which admin send request |  | Fixed | Critical | P1 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_136 | Reset Password | 1 | Password field is accepting same old password | The same password should not be accepted and error message should appear to set new password other than previous password | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_137 | Reset Password | 1 | After confirming the password user should not be redirected to the login page |  | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_138 | Skip turn | 1 | When the skip pop-up is open the profile image is different who turn is going to skip |  | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_139 | Chat Screen | 1 | If the user deletes the account while his turn going on then the other participants' chat screen grey mask appear |  | Fixed | Critical | P1 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_140 | Chat Screen | 1 | If the user deletes the account while his turn going on then rounds count becomes null |  | Fixed | Critical | P1 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_141 | Story Card | 1 | Please add the logo and app name in the story card in the first line |  | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-23 | Bug_142 | Story Card | 1 | Please add the app store and playstore icons in the bottom of the story card | Icons are looking lit bit blur...We can minimize the size of icons | Fixed | Low | P4 | 2024-03-26 | Saurabh, Komal |  | Done
2024-03-26 | Bug_143 | Forgot Password | 1 | After submitting the email id.In-App notification should have otp in uppercase letter i.e. OTP |  | Fixed | Low | P4 |  | Saurabh, Komal |  | Done
2024-03-26 | Bug_144 | My Account | 1 | The email Field should be added above the mobile field...It should show the email ID that is registered while creating account | Note: It should not be editable for any users | Fixed | Low | P4 | 2024-03-27 | Saurabh, Komal |  | Done
2024-04-01 | Bug_145 | My Account | 1 | Both First and Last names accept details less than 4 characters | Please show the alert message...Just like added in sign up page for not accepting characters less than 4 | Fixed | Low | P4 |  | Saurabh, Komal